## Sheet1
www.capoministrysolutions.com
WEEK | Creative Team | Scheduling | Video | Media | Music/Tech | Promotion | Set Design | Special Elements
8 | series branding, layout
7
6 | discussion message theme
5* | plan service/assign leaders
4 |  | scheduling first wave
3* | materials to team | scheduling second wave
2 | rough drafts due (video, scripts)
1* | final details (message slides, print)
| *every ministry has a different workflow. Fill in due dates for all plans, materials, content, etc, in a way that will work for you and your team. However, one of the purposes of filling out this chart and following it as a team is to get ahead on critical deadlines in order to help your creative team run more smoothly, to stay ahead of the game. To that end, pull back your service planning as far as you are able, allowing your team the most time possible to complete their tasks. I've left in a few critical deadlines we follow at my own ministry as a benchmark. These deadlines really help us stay ahead, keep the quality level high, and avoid panic. -Jim Jensen |  | Items that could appear on this workflow: Series Branding/Development Message Theme Service Planning Final Details Scheduling Deadlines When someone is assigned to lead a service element (giveaways, props, videos, etc.) Storyboarding/Writing Finding actors or real life stories to share live or on video Filming/Editing Rought Drafts Final Drafts Series Graphics Service Graphics/Slides Lyric/Message Slides Countdowns/Bumpers Announcement Scripts Music Selection MP3s, Music Charts Singer Assignments Band Notes/Stage Notes/Stage Setup Lighting Design Stage Plot Program/Bulletin layouts Printing Service Document Distribution (service orders, stage plots, scripts, etc) Set Design Ideas Blueprints/Materials